27/09/2004

AGREEMENT BETWEEN: EPSILON INDUSTRIKONSTRUKTIONER AB AND AP GLOBAL SALES AB:

CLIENT:  		Managing Director

COACH:		Salome van Coller-Peter

DIRECT STAKEHOLDERS:  Ingemar Andreasson

Executive team of the client-organisation.

CLIENT-ORGANISATION:   Epsilon Industrikonstruktioner AB

DATE OF AGREEMENT:      7 October 2004

LIST OF CONTENTS			PAGE NUMBERS

Title					2

Aims					2

Outcomes					2

Scope					3

Project Feasibility				6

Impact of project-results on the client-organisation		8

Attachments:

- Process-flow-diagram indicating project actions and times.	9

- Glossary of terms.				10

DESCRIPTION OF PROJECT TO BE DELIVERED:

(Read in conjunction with glossary of terms – attached)

Project Title:

The use of coaching to obtain agreement regarding the preferred culture within the executive team of the client-company.

Project Aims:

To investigate the use of coaching to facilitate agreement, amongst

all members of an executive team, regarding the preferred culture in

the organisation.

To map out the coaching steps developed in the process of

facilitating agreement amongst all members of an executive

team, regarding the culture that they prefer to have in their organisation.

To investigate, through coaching, those indicators which reflect both

existing- and preferred cultures of the organisation.

Project outcomes:

Better understanding of company culture and specifically the four main cultures, described by Roger Harrison and the feasibility of having a combination of cultures in one organisation.

Increased awareness regarding the perceptions of executives on other levels of the organisation regarding both the current and preferred cultures of the Epsilon Industrikonstruktioner AB.

An agreed preferred culture agreed upon by all the members of the executive team.

Increases personal understanding of individual versus team perceptions of the preferred organisational culture.

A list of personal- and team indicators that would reflect the preferred culture within the company.

A set of personal (individual) and a set of team goals aimed at the implementation of indicators that would facilitate positive growth towards the development of the team’s preferred culture.

Project Scope:

The scope of work will be focused mainly on the executive team of the client-company.  Another team of Epsilon-staff members on lower levels of the organisation will be included in the cultural survey part of the project for the purposes of comparison regarding the existing and preferred cultures in the organisation.

Roger Harrison’s diagnostic cultural questionnaire will be used to identify the existing and preferred cultures within the organisation.

A coaching-process will be developed, consisting of both group and individual coaching interventions, aimed at:

- Ensuring buy-in and commitment to the complete research process;

- Facilitating understanding of the four cultures measured by the Roger Harrison cultural questionnaire.

- Establishing meaning of own versus team perceptions of culture and values

- Reaching agreement regarding the preferred culture in the organisation and

- Exploring indicators that reflect the preferred culture.

Roles to be played by the coach:

- Facilitator - of group processes aimed at discovering, discussing, understanding and deciding the cultural indicators of the company culture.

- Trainer - a questionnaire will be used to determine both the existing and preferred cultures within the executive team. Team members will need specific knowledge and skills to complete, score and interpret the results, and even more importantly, to understand the results.

- Coach - supporting the group and individuals within it, helping them reflect on the meaning of values and behaviours (beliefs, sentiments, emotions and actions).

Relationship of the coach to client-company:

The position of the coach will be that of an independent outsider.

The client-company will hire the coach for one year only.

The coach does not wish to become an employee, but would like to conduct and conclude the research necessary for the completion of the coach’s doctorate in executive coaching/professional studies.  The research conducted in this organisation will form part of the package for which the coach will be paid.  The coach is thus not an insider researcher; this is the continuation of a relationship which started two years ago, and is based on mutual goodwill and recognition of the achievement we have made together to date.

Tools and techniques used to collect and analyse data:

- Questionnaire on Organizational Culture by Roger Harrison:

Two sample-groups will complete a questionnaire to diagnose the organisation’s culture- the executive team of the Epsilon-company and another, randomly chosen group of executives on lower levels of the client-company.

The rationale behind this is that the executive core of the organisation should be able to compare its views with those of its internal customers (employees) so as to determine any significant gaps in perception.  However, only the executive team will be included in the coaching-intervention.

- Coaching:

For the purposes of this research, a coaching-process is to be devised that will foster agreement amongst the members of an executive team as to their preferred organizational culture.

To achieve this, a combination of group and individual coaching sessions will

be held.

- Group coaching will be used as the means through which the values of the executive team, as it is reflected in the culture-questionnaire, will be confirmed. The values of both the existing and preferred cultures apply.

- Group coaching will also verify the behaviours that underpin the values reflected by both the existing and preferred cultures.

- Individual coaching sessions will be held to increase understanding of the research process, to ensure support for it and establish goodwill with every member of the executive team.

- Individual coaching sessions will be held for the purposes of establishing meaning of the individual’s personal values, and how these relate to the values of the group.

- Research Diary:

A research diary will be kept to log significant experiences and insights prior to, during and after research, facilitation and coaching sessions.  Furthermore, participants who receive coaching will be asked to keep a diary describing their own experiences of the process.  I hope that the involvement of participants throughout the whole process will provide the necessary incentive for them to log significant and useful data.  I also hope that participant’s diaries will reveal the writer’s angle on events and the feelings they have had in relation to them.  It should also give insight into the coaching-process.

Triangulation is achieved since the three main methods of data-collection (described above) should facilitate objectivity and reduce bias.

Additional benefits to that of informing the client-organisation?

- Aligned thinking with regard to the future business of the organisation.

- Practical guidelines to all employees regarding the behaviour necessary to reach the organisation’s business goals.

- More awareness of the brand name which the company represents.

PROJECT FEASIBILITY:

The coach has the following necessary skills and knowledge to carry out this research in order to complete this project successfully?

Knowledge:

- How to properly apply Roger Harrison’s cultural questionnaire to ensure the collection of reliable data.

- How to analyse and interpret the data rendered by this questionnaire (data-analysis).

- How to give feedback to my stakeholders in a meaningful, practical and encouraging way.

- How to conduct group and individual coaching sessions.

Skills:

- Influencing skills to ensure that as many people as possible complete the surveys.

- Coaching skills.

- Communication, negotiation, convincing and persuasive skills.

- Instilling trust in people who have no reason to trust or mistrust me.

- Gaining the goodwill of all stakeholders.

- Facilitation and training skills.

Resources required to successfully implementing this project?

Human:

The Informed consent, (see glossary of terms) of the sponsor of this project (Managing Director of client-company).

Openness and Honesty, as well as the support of all the members, of the executive team of the client-organisation.

Time:

From January 2005 to November 2005

This timescale is realistic (see process-flow diagram)

To complete the project, six complete work weeks is needed, during 2005.

Typical schedule of a workweek:

Group coaching Monday morning (executive team and coach)

Individual coaching the rest of Monday, Tuesday and Friday (members of executive team one-on-one with coach).

Training days (Wednesday and Thursday).

The two days training per work week is reserved for project management training only.  Any other training necessary will be estimated at the consultancy rate mentioned under cost-heading.

Tentative dates:

Weeks 05-4, 05- 9, 05- 14, 05- 19, 05- 24 and 05-47.

Location:

Client’s premises (6 different business units situated in 6 different towns in Sweden) and coach’s office.

Information:

The main source of information will be the people that form part of this

project-process.  The biggest challenge for both coach and client will be

to gain and maintain the trust, support and goodwill of all key

key stakeholders involved in this project (executive team members).

Impact of project-results on the Client-organisation:

- A preferred culture, agreed by all members of the Executive team of the organisation.

- Enhanced understanding of the meaning of culture and values, especially those indicators which are indicative of a specific culture.

- Agreed cultural indicators of both the existing and preferred cultures with the Epsilon-company.

- Agreed executive team performance plan, specifying the indicators  necessary in order to facilitate growth towards the agreed preferred culture.

- Personal action plans, prepared by each individual member of the Executive-Team, describing how they will reach the agreed executive team performance plan.

- Enhanced awareness and understanding of the indicators/behaviour, which reflect the presence/existence of a particular culture.

Confidentiality:

Both parties agree that all information shared amongst the client, coach

and members of the executive team will be treated with respect.

Decisions regarding the sharing of information discussed amongst

coach, client and members of the executive team should carry the

consent of all the relevant stakeholders.

Payment terms:

As per receipt of invoice from AP Global Sales AB.

We hereby agree to the above on 7 October 2004.

CONFIDENTIAL		            SALOME VAN COLLER-PETER

Managing Director			Director of Development

Epsilon Industrikonstruktioner	AP Global Sales AB